## Slide 1: Teradata to Snowflake Migration
Project overview for the Deloitte Delivery Team

## Slide 2: Project Overview and Scope
Migrate the Cisco Enterprise Data Warehouse (EDW) from on-premise Teradata to the Snowflake cloud platform.
Largest AI & Data engagement at Cisco
7th largest deal for Snowflake’s fiscal 2026 (RPO of $133M over 3 years)
Scope: Only Wave 2 is in focus for this Statement of Work (SOW), which includes migrating all finance-related data pipelines and Business Objects (BO) applications required for finance functions. This is ~1/3rd of the overall scope.
Engagement Details:
    Current State: Teradata, INFA PC, BTEQs, Control-M, Business Objects (BO)
    Target State: Snowflake, DBT Models, Control-M/Airflow, BO
    Volumetrics: ~1,350 tables, 4,300 Informatica PowerCenter jobs (90% converted to BTEQ/SQL), 3 BO and 133K reports universes
    Approach: Lift and shift migration from Teradata to Snowflake
    Release Strategy: 3 release (1A, 1B and 1C). This will require forward and backward bridging. Avoid release in month 3 and FYQ4.
    Parallel Run: 3-month parallel run for each release. Must include quarter end
    Snowflake Setup: Account setup, RBAC, cataloging, administration, etc. will be Cisco’s responsibility
    Ingestion: Cisco’s custom ingestion framework CCI will be used for repointing ingestion from Teradata to Snowflake
    GCP BQ Dependency: Common Hierarchies and gross ARR are on GCP BQ and are being replicated to Snowflake
    Downstream Applications: Testing will be Cisco’s responsibility. Minimize the impact on downstream applications – keys need to be same
Acceptance Criteria (Success Measures):
    100% of in-scope pipelines and up to 200 BO reports tested in Snowflake UAT
    100% data parity between Teradata and Snowflake excluding mutually agreed up exceptions
    ≥10% average ETL/report performance improvement over Teradata. No refactoring.
    0 open Severity 1 defects at production cutover
    Full stakeholder (Cisco) sign-off on each deliverable/milestone—deficiencies are to be promptly resolved at Supplier cost
Cisco awarded us the contract, even though our fees were ~40% higher than those of the competition.

## Slide 3: Project Timeline
Severe financial implications of missing timelines
Key Milestones
    Phase out GCP BigQuery: Marked at Q1 FY27 (Sep–Oct 2026)
    Project must be completed (all waves) before end of Aug ’27.
    Hard deadline to decouple from Teradata by Nov ‘27.
    Shutdown Teradata: Marked at Q2 FY28 (Jan–Feb 2028)
Future Pipeline
    Delivery excellence of wave 2 will lead to we getting wave 3 and 4 (~200% of wave 2 scope)
    Other opportunities depend on the execution of wave 2 (AI COE, FP&A Management Reporting, etc.)

## Slide 4: Migration Approach
Continuous Delivery of Domain Applications
We bring market leading automation across each of the implementation phases to successfully deliver.
ENTERPRISE DATA ANALYTICS AND MODERNIZATION – AUTOMATION LED APPROACH
Iteratively migrate use cases/data domains to production for in scope wave 2 workloads
Program Management & Governance
Establish the key functions required to govern program strategy and execution, manage staffing needs, monitor delivery progress and quality, and provide change management support
Establish Foundation
Modernization PODs
Domain PODs
Other PODs
Pool of SMEs
(Platforms, Tools, Domain etc.)
Foundation Services (Refactor)
Conformed Data Model
Integration Patterns
Updated Migration Roadmap and Refined Future State Architecture
AWS/Snowflake/Informatica/DBT/BO Center of Excellence
(Automation frameworks)
MVP Use Case Implementation
Implement: Minimum Viable Product (“MVP”) – “Expenses”
1b
Parallel Runs
The execution of parallel runs for ETL pipelines and data reconciliation between Teradata and Snowflake .
Hypercare
Provide support to ensure SLAs are met, resolve any defects, and stabilize operations. Address any defects promptly and confirm closure only after all critical issues are resolved and plan for handover to Data Ops.
Parallel Run, Data Ops, Hypercare
Integration Management
Adoption of Future Target State Platform
Scale-out: Enhance and Optimize
3
Agile Delivery
Dev Ops
Enable new capabilities
Execution Model (Delivery PODs)
Audit, Balance & Control Framework
Automation Frameworks
Data Certification
Data Security enabled
Prioritize Use Cases, Enterprise and Domain Assets and Source Systems
Incorporate dependencies and co-relationships between data and Domains Assets
Migration assessment, Roadmap and plan, Validate use case and data domain tranches
Future State Architecture
Current State Architecture
Discovery and Migration Planning
1a
Technology Blueprinting
Technology Tooling Options
Upstream & Downstream dependencies
Automation Framework evaluation
Data Mgmt. & Security
Governance & Security
2

## Slide 5: Summary of All Accelerators to be leveraged for Snowflake Migration
Accelerator | Purpose | Migration Design and Plan | MVP | Re-platform | Testing
Deloitte Informatica Parser | Parsing of Informatica Jobs to separate mappings and database native code |  |  |  | 
Deloitte ETL Reverse Engineering | Dependency and Complexity Analysis, Scope Confirmation and Source to Target Mapping |  |  |  | 
Snowflake SnowConvert AI | Teradata Object Conversion Coverage and Efficiency Analysis during Migration Design and Plan and Conversion of Teradata database objects (tables, views, SQLs, BTeQs, Stored Procedures, etc.) to Snowflake objects during MVP and Re-platform |  |  |  | 
Deloitte ETL Code Converter | Conversion of Informatica mappings to SnowSQL |  |  |  | 
Deloitte DBT Code Converter v1 | ETL pipelines conversion to DBT (SnowSQL) |  |  |  | 
Deloitte DBT Code Converter v2 | ETL pipelines conversion to DBT Models |  |  |  | 
Deloitte Orchestration Agent | Agent to orchestrate ETL Code Conversion |  |  |  | 
Cisco CCI | Data migration from Teradata to Snowflake |  |  |  | 
Deloitte ETL Code Tester | Data testing tool for data parity testing, data reconciliation and validation |  |  |  | 
Deloitte DRECT | Report Reconciliation, Validation & Testing |  |  |  | 

## Slide 6: Discovery and Migration Planning
This is a foundational step in migrating from Teradata to Snowflake. This phase focuses on doing a discovery to confirm the scope, dependencies, complexities, architecture, constraints and priorities for the migration. The goal is to develop a roadmap, detailed execution plan and MVP scope.
Legend:
Cisco
Deloitte
Assess
Dimensions for Assessment
Volume of objects and workloads
Scope
Dependencies and Complexities
Architecture & Tech BOM
Technical Debt
Accelerator Efficiencies
Non-functional Requirements
Complexity Analysis Report
Projected Accelerator Efficiency Report
MVP Scope
Re-platform Roadmap
Migration Plan
Effort Estimation
Technical Debt Remediation Plan
Cisco Dependencies
Non-functional Requirements
Deliverables/Outcomes
Dimensions for Assessment
Migration Scope and Backlog Validation
1
Accelerators
Purpose
Accelerators
Separate Informatica XML & DB native code
Conversion efficiency Teradata Code to SnowSQL
Informatica Parser
Dependency and Complexity Analysis
ETL Reverse Engineering
SnowConvert AI
Input
Business Imperatives
Priorities
Constraints
Domains & Use Cases
Technical Objects
Database Objects
ETL Objects
Reporting Objects
Job Orchestration
Accelerators and Access
Accelerators Setup
Developer Access
Business Functions & Downstream Apps.
Business Functions
Downstream Apps

## Slide 7: Implement Minimal Viable Product (“MVP”)
Conduct an end-to-end MVP migration to validate the coverage and efficiency of accelerators for Cisco. Outcomes and lessons learned from this phase will help us refine the overall migration roadmap and timeline, if necessary. We will use Expenses for the MVP.
Legend:
Cisco
Deloitte
Deliverables/Outcomes
MVP
Accelerator Efficiency Report
Effort Estimation
Re-platform Backlog and Plan
Migration Roadmap
Accelerator Usage Recommendations
Resourcing and PODs
Testing and Implementation Accelerator Setup
Accelerator Enhancements Backlog
Dimensions for Assessment
Assess
Dimensions for Assessment
Volume of objects and workloads
Scope
Dependencies and Complexities
Architecture & Tech BOM
Technical Debt
Accelerator Efficiencies
Non-functional Requirements
Accelerators
Purpose
Accelerators
Convert SnowSQL code to DBT
Convert Teradata Code to SnowSQL
Historical Data Migration
Separate Informatica XML & DB native code
Convert INFA XML code to SnowSQL
Orchestrate accelerators to reduce manual intervention
SnowConvert AI
CCI
Informatica Parser
ETL Code Converter
Orchestration Agent
DBT Code Converter v1
DBT Code Converter v2
Input
MVP environment
Accelerators
Instantiated Architecture
Developer Access Provisioned
MVP scope
Database Objects
ETL Objects
Reporting Objects
Job Orchestration
Roadmap and Estimation
Effort Estimation
Roadmap
Accelerators
Projected Accelerator Efficiencies

## Slide 8: Scale-out – Re-platform, Enhance and Optimize (Track 1A, 1B, 1C)
Using the updated migration, Scale-out Phase starts execution of the migration roadmap to re-platform from Teradata to Snowflake using a POD based delivery model.
Legend:
Cisco
Deloitte
Assess
Dimensions for Assessment
Conversion Accuracy
Delivery Velocity
Accelerator Efficiencies
Non-functional Requirements
Teradata & Snowflake Difference Impact
SIT Readiness
BAT Test Plans
Input
Development environment
Accelerators
Instantiated Architecture
Developer Access Provisioned
Re-platform scope
Database Objects
ETL Objects
Reporting Objects
Job Orchestration
Ingestion Repointing
Non-Functional Requirements
Benchmarks & SLEs/SLAs
Accelerators
Purpose
Accelerators
Convert INFA XML code to SnowSQL
Convert Teradata code to SnowSQL
Orchestrate accelerators to reduce manual intervention
Historical data migration
Data testing tool for data parity testing
Automated report testing
Convert SnowSQL code to DBT
ETL Code Converter
SnowConvert AI
Data Assist Orchestration Agent
CCI
ETL Code Tester
DRECT
DBT Code Converter v1
DBT Code Converter v2
Deliverables/Outcomes
Repointed Ingestion
Converted ETL Pipelines
Unit Testing Results
History Data Migration for SIT
SIT Test Plan
SIT Test Cases
Dimensions for Assessment
ETL/ELT Conversion Package
2
Orchestration Package
3
Business Objects Application Conversion Package
4

## Slide 9: Parallel Run, Data Ops, Optimize (Track 1A, 1B, 1C)
Perform automation-led SIT and BAT using set-based, exception-based testing approach. Monitor performance and optimize prioritized workloads to meet SLEs/SLAs.
Legend:
Cisco
Deloitte
Assess
Dimensions for Assessment
Conversion Accuracy
Results Comparison to Legacy
Defect Severity and Volume
Non-functional Requirements
Teradata & Snowflake Difference Impact
Performance Benchmarks
Report Reconciliation
Accelerators
Purpose
Accelerators
Convert Teradata code to SnowSQL
Convert SnowSQL code to DBT
SnowConvert AI
Historical data migration
CCI
Orchestrate accelerators to reduce manual intervention
Orchestration Agent
Data testing tool for data parity testing
ETL Code Tester
Automated report testing
DRECT
DBT Code Converter v1
DBT Code Converter v2
SIT Testing Results
BAT Testing Results
Performance Testing Results
Defect Prioritization and Resolution Report
Data Reconciliation Report
Deliverables/Outcomes
Dimensions for Assessment
Data Validation and Sign-off
5
Orchestration Package
3
ETL/ELT Conversion Package
2
Final Documentation Package
6
Business Objects Application Conversion Package
4
Input
Test Environment & Data
Teradata & Snowflake Test Bed
Incremental Loads Data
BAT Test Plans
Testing Scope
Database Objects
ETL Objects
Reporting Objects
Job Orchestration
Ingestion Repointing
Performance
Non-Functional Requirements
Benchmarks & SLEs/SLAs

## Slide 10: Key Deliverables & Milestones
Deliverables by phase
Migration Plan and Backlog Validation | Develop migration plan, map dependencies, validate inventory, create MVP scope and sprint roadmap for Wave 2 (Tracks 1A, 1B &1C) | Roadmap finalized, plan signed off, all planning tasks complete
ETL/ELT Conversion Package | Migrate and optimize Teradata scripts, Informatica jobs, UDFs, and views for Snowflake compatibility; validate execution in test/BAT environments. | Conversion of all in-scope ETL/ELT jobs to Snowflake
Orchestration Package | Build DBT models, configure Control-M jobs, document dependencies | Control-M jobs operational in test, dependencies & schedule validated
Business Object Application conversion package | Convert BO universes/reports to Snowflake, adapt IAM security | Reports equivalent, improved runtime, validated security controls
Data Validation & Signoff | Perform unit/integration/BAT, data lineage reconciliation, stakeholder validation | The goal is 99.5%* data reconciliation; any mismatches will be analyzed and documented
Final Documentation Package | Prepare migration, validation, lineage docs, post-cutover/support materials | Editable docs delivered, summary/support guides ready
Parallel Run, Data Ops, Optimize
Scale-out – Re-platform, Enhance and Optimize
Migration Design and Plan
Note: 99.5% data parity to be targeted for critical data entities
02
03
04
05
06
01
Deliverables
Critical Activities
Outcomes/Acceptance Criteria

## Slide 11: Team Organization
Our joint team combines Cisco’s deep knowledge of its current capabilities, pain points, and aspirations with Deloitte’s experienced specialists – including many whom you already know and trust.
Cisco Enterprise Architect Product Owner | Deloitte Solution Architect Data Architect
PROGRAM LEADERSHIP
Cisco Program Manager | Deloitte Lead Engagement Partner Technical Leader
Cisco Product Owners | Deloitte Program Manager Delivery Leader
PROJECT MANAGEMENT
ARCHITECTS
REPORTING POD
QA POD
Cisco Business Analyst Product Owner | Deloitte Reporting Lead Reporting Engineer 1 Reporting Engineer 2
DATA POD 1
Cisco Business Tester BAT Lead | Deloitte Testing Lead Test Engineer 1 Test Engineer 2 Test Engineer 3 Test Engineer 4
Cisco Business Analyst | Deloitte Data Engineer Lead Data Engineer 1 Data Engineer 2 Dev Ops Engineer 1
Deloitte Data Engineer Backend API Engineer AI Engineer
INNOVATION POD
CISCO EXECUTIVE SPONSORS
DELOITTE EXECUTIVE SPONSORS
STEERING COMMITTEE
RISK AND QUALITY
Cisco Internal QA | Deloitte QA
CORE DELIVERY POD
DATA POD 2
Cisco Business Analyst | Deloitte Data Engineer Lead Data Engineer 1 Data Engineer 2 Dev Ops Engineer 1
DATA POD 3
Cisco Business Analyst | Deloitte Data Engineer Lead Data Engineer 1 Dev Ops Engineer 1
Cisco PMO Change Coordinator | Deloitte PMO – Onshore PMO – Offshore
Cisco Business Analyst Product Owner | Deloitte Data Lead - 1 Data Lead - 2 Data Lead - 3 Reporting Tech Lead Data Engineer AI Architect
Discovery

## Slide 12: Key Stakeholders
Here are the key Cisco stakeholders
Stakeholder | Title/Role | Description
Nilesh Kulkarni | VP of Data Analytics | 
Chiranjeevi Koyi (Chiru) | Director: Data Engineering | 
Virendra Singh | Director, Data Platforms | 
Harish Sabhnani | Data Platforms Leader | On Virendra’s team. We will work very closely with Harish.
Terence O’Donovan | IT Architect | 
Devi Kumarappan | Director, Engineering: CX Data Platform and Operations |